## Sheet
Epic / Week | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Project Setup | Week 1: ███████
Authentication & Authorization | Week 1: ███████
Home Page | Week 2: ███████; Week 3: ███████
Job Detail Page | Week 3: ███████; Week 4: ███████; Week 5: ███████
Subject Area Module | Week 5: ███████
Jobs List Module | Week 6: ███████
Change Requests Module | Week 6: ███████
ServiceNow Module | Week 6: ███████
Reports Module | Week 7: ███████
Settings Module | Week 7: ███████; Week 8: ███████
API Integration | Week 8: ███████
Testing | Week 9: ███████
Documentation | Week 9: ███████
Deployment | Week 10: ███████
Project Closure | Week 10: ███████