## Sheet
Epic | ID | User Story | Tasks/Subtasks | Acceptance Criteria | Priority | Story Points | Sprint Number | Assignee
Project Setup | 1 | As a project manager, I want to define the project scope so that all stakeholders have a clear understanding of the deliverables. | Review FRD and identify key deliverables | Scope Document is created and includes all key deliverables. | High | 3 | 1 | Team Member 1
Project Setup | 2 | As a project manager, I want to define the project scope so that all stakeholders have a clear understanding of the deliverables. | Identify in-scope and out-of-scope functionalities | Scope Document clearly defines what is in-scope and out-of-scope. | High | 2 | 1 | Team Member 2
Project Setup | 3 | As a project manager, I want to define the project scope so that all stakeholders have a clear understanding of the deliverables. | Obtain sign-off on scope from stakeholders | Stakeholders have signed off on the scope document. | High | 1 | 1 | Team Member 3
Project Setup | 4 | As a project manager, I want to create a detailed project schedule so that we can track progress and meet deadlines. | Create a detailed project schedule | Project Schedule (Gantt Chart) is created with all tasks and timelines. | High | 3 | 1 | Team Member 1
Project Setup | 5 | As a project manager, I want to create a detailed project schedule so that we can track progress and meet deadlines. | Assign tasks and responsibilities to team members | Responsibility Assignment Matrix is created with clear task assignments. | Medium | 2 | 1 | Team Member 2
Project Setup | 6 | As a project manager, I want to create a detailed project schedule so that we can track progress and meet deadlines. | Establish communication and reporting protocols | Communication Plan is created outlining communication channels and frequency. | Medium | 1 | 1 | Team Member 3
Project Setup | 7 | As a developer, I want to set up the development environment so that I can start coding. | Provision necessary hardware and software | Development Environment Setup is complete and accessible. | High | 3 | 2 | Team Member 1
Project Setup | 8 | As a developer, I want to set up the development environment so that I can start coding. | Configure version control system (Git) | Git Repository is set up and accessible for version control. | High | 2 | 2 | Team Member 2
Project Setup | 9 | As a developer, I want to set up the development environment so that I can start coding. | Set up testing and staging environments | Testing and Staging Environments are set up and configured. | Medium | 2 | 2 | Team Member 3
Authentication & Authorization | 10 | As a user, I want to be able to log in using Okta single sign-on so that I don't have to remember multiple passwords. | Integrate Okta for single sign-on | Okta Integration Document is created. | High | 3 | 2 | Team Member 1
Authentication & Authorization | 11 | As a user, I want to be able to log in using Okta single sign-on so that I don't have to remember multiple passwords. | Test Okta authentication flow | Working Okta Authentication is verified. | High | 2 | 2 | Team Member 2
Authentication & Authorization | 12 | As an administrator, I want to implement role-based access control so that users only have access to the features they need. | Define user roles and permissions (Admin, Developer, Read-Only, Support Engineer) | RBAC Matrix is created defining roles and permissions. | High | 3 | 3 | Team Member 3
Authentication & Authorization | 13 | As an administrator, I want to implement role-based access control so that users only have access to the features they need. | Implement RBAC logic in the application | RBAC Implementation is implemented in the application. | High | 3 | 3 | Team Member 1
Authentication & Authorization | 14 | As an administrator, I want to implement role-based access control so that users only have access to the features they need. | Test user roles and permissions | Verified RBAC Implementation confirms users have correct access. | High | 2 | 3 | Team Member 2
Data Layer - Snowflake | 15 | As a developer, I want to set up the Snowflake connection so that I can access data. | Establish connection to Snowflake database | Snowflake Connection String is created and tested. | High | 2 | 3 | Team Member 3
Data Layer - Snowflake | 16 | As a developer, I want to implement the data model in Snowflake so that the data is organized correctly. | Data Model Implementation | Data Model Schema is implemented in Snowflake. | High | 3 | 4 | Team Member 1
Data Layer - Snowflake | 17 | As a data engineer, I want to create data extraction scripts so that I can pull data from Snowflake. | Create scripts to extract necessary data from Snowflake | Data Extraction Scripts are created and functional. | High | 3 | 4 | Team Member 2
Data Layer - Snowflake | 18 | As a data engineer, I want to create data extraction scripts so that I can pull data from Snowflake. | Test data extraction scripts | Verified Data Extraction Scripts ensures data is extracted correctly. | High | 2 | 4 | Team Member 3
Data Layer - External APIs | 19 | As a developer, I want to integrate with the ServiceNow API so that I can fetch incident and change request data. | Obtain API access to ServiceNow for Incidents and Change Requests | ServiceNow API Credentials are obtained. | Medium | 1 | 4 | Team Member 1
Data Layer - External APIs | 20 | As a developer, I want to integrate with the ServiceNow API so that I can fetch incident and change request data. | Implement API calls to fetch Incidents and Change Requests | ServiceNow API Integration Code is implemented. | High | 3 | 4 | Team Member 2
Data Layer - External APIs | 21 | As a developer, I want to integrate with the UC4 API so that I can fetch job and job plan data. | Obtain API access to UC4 for job and job plan data | UC4 API Credentials are obtained. | Medium | 1 | 5 | Team Member 3
Data Layer - External APIs | 22 | As a developer, I want to integrate with the UC4 API so that I can fetch job and job plan data. | Implement API calls to fetch job and job plan data | UC4 API Integration Code is implemented. | High | 3 | 5 | Team Member 1
Data Layer - Data Transformation | 23 | As a data engineer, I want to implement data transformation logic so that the data is in the required format. | Transform data extracted from Snowflake and APIs into the required format | Data Transformation Scripts are created. | High | 3 | 5 | Team Member 2
Data Layer - Data Transformation | 24 | As a data engineer, I want to implement data transformation logic so that the data is in the required format. | Test data transformation logic | Verified Data Transformation Scripts confirms data transformation is correct. | High | 2 | 5 | Team Member 3
Home Module | 25 | As a user, I want to be able to search for jobs so that I can quickly find the information I need. | Create UI for job search | Search UI Component is created. | High | 2 | 5 | Team Member 1
Home Module | 26 | As a user, I want to be able to search for jobs so that I can quickly find the information I need. | Implement backend logic for job search | Working Job Search functionality is implemented. | High | 3 | 6 | Team Member 2
Home Module | 27 | As a user, I want to see a list of subject areas so that I can easily navigate to different sections of the application. | Create UI for subject area list | Subject Area List UI Component is created. | Medium | 2 | 6 | Team Member 3
Home Module | 28 | As a user, I want to see a list of subject areas so that I can easily navigate to different sections of the application. | Fetch subject area data from database | Subject Area List Data is fetched from the database. | Medium | 2 | 6 | Team Member 1
Home Module | 29 | As a user, I want to see recent incidents so that I can stay informed about system issues. | Create UI for recent incidents | Recent Incidents UI Component is created. | Medium | 2 | 6 | Team Member 2
Home Module | 30 | As a user, I want to see recent incidents so that I can stay informed about system issues. | Fetch recent incident data from database | Recent Incidents Data is fetched from the database. | Medium | 2 | 6 | Team Member 3
Home Module | 31 | As a user, I want to see change requests so that I can stay informed about system changes. | Create UI for Change Requests | Change Requests UI Component is created. | Medium | 2 | 7 | Team Member 1
Home Module | 32 | As a user, I want to see change requests so that I can stay informed about system changes. | Fetch Change Request data from database | Change Request Data is fetched from the database. | Medium | 2 | 7 | Team Member 2
Dashboard Module | 33 | As an operator, I want a system health overview dashboard so that I can quickly identify potential problems. | Design and develop system health overview dashboard | System Health Overview Dashboard UI is created. | High | 3 | 7 | Team Member 3
Dashboard Module | 34 | As an operator, I want a system health overview dashboard so that I can quickly identify potential problems. | Fetch and display system health metrics | System Health Metrics Data is displayed on the dashboard. | High | 3 | 7 | Team Member 1
Dashboard Module | 35 | As an operator, I want to see alerts so that I can be notified of critical issues. | Design and develop alerts section | Alerts UI Component is created. | High | 2 | 7 | Team Member 2
Dashboard Module | 36 | As an operator, I want to see alerts so that I can be notified of critical issues. | Implement logic for displaying alerts | Alerts Data is displayed in the alerts section. | High | 3 | 8 | Team Member 3
Dashboard Module | 37 | As an operator, I want to see key metrics so that I can monitor system performance. | Design and develop key metrics section | Key Metrics UI Component is created. | Medium | 2 | 8 | Team Member 1
Dashboard Module | 38 | As an operator, I want to see key metrics so that I can monitor system performance. | Fetch and display key metrics data | Key Metrics Data is displayed in the key metrics section. | Medium | 2 | 8 | Team Member 2
Job Scheduler Module | 39 | As a User, I want Job Scheduler Screen. | Design the Job Scheduler screen layout | Job Scheduler Screen Mockup is created | High | 2 | 8 | Team Member 3
Job Scheduler Module | 40 | As a User, I want Job Scheduler Screen. | Develop the Job Scheduler screen UI | Job Scheduler UI Component is created | High | 3 | 8 | Team Member 1
Job Scheduler Module | 41 | As a User, I want Filter Bar Functionality. | Develop Date Range Picker | Date Range Picker Component is developed | High | 2 | 9 | Team Member 2
Job Scheduler Module | 42 | As a User, I want Filter Bar Functionality. | Develop Environment Dropdown | Environment Dropdown Component is developed | High | 2 | 9 | Team Member 3
Job Scheduler Module | 43 | As a User, I want Filter Bar Functionality. | Implement Apply and Reset Buttons functionality | Working Apply/Reset Buttons functionality | High | 2 | 9 | Team Member 1
Job Scheduler Module | 44 | As a User, I want Search Functionality. | Develop Global Search Bar | Global Search Bar Component is developed | High | 2 | 9 | Team Member 2
Job Scheduler Module | 45 | As a User, I want Search Functionality. | Develop Job List Search | Job List Search Functionality is developed | High | 3 | 10 | Team Member 3
Job Scheduler Module | 46 | As a User, I want Job Listing Table. | Implement Pagination | Pagination Component is implemented | High | 3 | 10 | Team Member 1
Job Scheduler Module | 47 | As a User, I want Job Listing Table. | Implement Sorting | Sorting Functionality is implemented | High | 3 | 10 | Team Member 2
Job Scheduler Module | 48 | As a User, I want Job Listing Table. | Display Columns (Job Name, Job Plan, Job Type, Description, Environment, Last Run) | Job Listing Table with Required Columns is displayed | High | 2 | 10 | Team Member 3
Job Scheduler Module | 49 | As a User, I want Hyperlink Behavior. | Implement Job Name Hyperlink to Job Detail Page | Job Name Hyperlink is implemented | High | 1 | 11 | Team Member 1
Job Scheduler Module | 50 | As a User, I want Hyperlink Behavior. | Implement Job Plan Hyperlink to Job Plan Detail Page | Job Plan Hyperlink is implemented | High | 1 | 11 | Team Member 2
Job Scheduler Module | 51 | As a User, I want UI/UX Requirements. | Implement Description field wrapping and truncation | Description Field Wrapping is implemented | High | 1 | 11 | Team Member 3
Job Scheduler Module | 52 | As a User, I want UI/UX Requirements. | Implement Responsive Layout | Responsive Layout Implementation is implemented | High | 2 | 11 | Team Member 1
Job Scheduler Module | 53 | As a User, I want Backend Filtering. | Optimize backend filtering for performance | Optimized Backend Filtering is done | High | 2 | 12 | Team Member 2
Job Scheduler Module | 54 | As a User, I want API Queries. | Implement API queries with filter, sort, and pagination parameters | Working API Queries is created | High | 3 | 12 | Team Member 3
Job Scheduler Module | 55 | As a User, I want Security and Access Control. | Ensure authorized users can view job data | Secure Job Data Access is implemented | High | 3 | 12 | Team Member 1
Job Detail Page Module | 56 | As a User, I want Header Section. | Display full technical job name as page title | Page Title is displayed | High | 1 | 12 | Team Member 2
Job Detail Page Module | 57 | As a User, I want Job Metadata Section. | Display Job Name, Job Type, Environment, Workflow, Last Run Status | Job Metadata Section is displayed | High | 3 | 13 | Team Member 3
Job Detail Page Module | 58 | As a User, I want Description Section. | Display job's functionality and schedule details | Description Section is displayed | High | 3 | 13 | Team Member 1
Job Detail Page Module | 59 | As a User, I want Tabs Section. | Implement tabs for Support Instructions, Job Plans, Run Stats, Incidents, Change Request | Tabbed Navigation is implemented | High | 3 | 13 | Team Member 2
Job Detail Page Module | 60 | As a User, I want Default Tab Load. | Set Support Instructions as default tab | Default Tab Loading is implemented | High | 1 | 13 | Team Member 3
Job Detail Page Module | 61 | As a User, I want Dynamic Content Loading. | Ensure each tab loads its data dynamically | Dynamic Content Loading is implemented | High | 2 | 14 | Team Member 1
Job Detail Page Module | 62 | As a User, I want Hyperlink Behavior. | Implement Workflow field hyperlink | Workflow Hyperlink is implemented | High | 1 | 14 | Team Member 2
Job Detail Page Module | 63 | As a User, I want Hyperlink Behavior. | Implement Document hyperlinks | Document Hyperlinks is implemented | High | 1 | 14 | Team Member 3
Job Detail Page Module | 64 | As a User, I want UI/UX Requirements. | Implement card-based layout, environment labels, word wrapping | UI/UX Improvements are implemented | High | 2 | 14 | Team Member 1
Job Detail Page - Support Instructions | 65 | As a User, I want SLA Display. | Display SLA in top-right corner | SLA Display is implemented | High | 1 | 15 | Team Member 2
Job Detail Page - Support Instructions | 66 | As a User, I want Restart Instructions. | Display restart steps as multi-line paragraph | Restart Instructions are displayed | High | 2 | 15 | Team Member 3
Job Detail Page - Support Instructions | 67 | As a User, I want Input Details. | Display input details as bullet points or comma-separated list | Input Details are displayed | High | 2 | 15 | Team Member 1
Job Detail Page - Support Instructions | 68 | As a User, I want Output Details. | Display output details including locations/destinations | Output Details are displayed | High | 2 | 15 | Team Member 2
Job Detail Page - Support Instructions | 69 | As a User, I want Support Notes. | Display support notes and guidelines | Support Notes are displayed | High | 2 | 16 | Team Member 3
Job Detail Page - Support Instructions | 70 | As a User, I want Exceptions for Non-Production Environments. | Display environment-specific instructions | Non-Production Exceptions are displayed | High | 2 | 16 | Team Member 1
Job Detail Page - Support Instructions | 71 | As a User, I want Schedule Frequency. | Display the job schedule frequency | Schedule Frequency is displayed | High | 1 | 16 | Team Member 2
Job Detail Page - Support Instructions | 72 | As a User, I want Linked Support Document. | Display and link the support document | Linked Support Document is displayed | High | 1 | 16 | Team Member 3
Job Detail Page - Support Instructions | 73 | As a User, I want Secured Access to Linked Documents. | Ensure secure access to PDF | Secured Document Access is implemented | High | 2 | 17 | Team Member 1
Job Detail Page - Job Plans Tab | 74 | As a User, I want Header Section. | Implement Tabs Navigation | Tab Navigation is implemented | High | 1 | 17 | Team Member 2
Job Detail Page - Job Plans Tab | 75 | As a User, I want Header Section. | Implement Search Field | Search Field is implemented | High | 2 | 17 | Team Member 3
Job Detail Page - Job Plans Tab | 76 | As a User, I want Job Plan Table. | Display Job Plan, Description, Environment, Last Modified Date columns | Job Plan Table is displayed | High | 3 | 17 | Team Member 1
Job Detail Page - Job Plans Tab | 77 | As a User, I want Pagination. | Implement Pagination | Pagination Controls are implemented | High | 2 | 18 | Team Member 2
Job Detail Page - Job Plans Tab | 78 | As a User, I want Environment Filter. | Implement Environment Filter | Environment Filter is implemented | High | 2 | 18 | Team Member 3
Job Detail Page - Job Plans Tab | 79 | As a User, I want Dynamic Content Loading. | Dynamically load job plans based on filters | Dynamic Job Plans Loading is implemented | High | 3 | 18 | Team Member 1
Job Detail Page - Job Plans Tab | 80 | As a User, I want Sorting. | Implement Sorting | Sorting Functionality is implemented | High | 2 | 18 | Team Member 2
Job Detail Page - Job Plans Tab | 81 | As a User, I want Hyperlink Behavior. | Implement hyperlink on Job Plan name | Job Plan Hyperlink is implemented | High | 1 | 19 | Team Member 3
Job Detail Page - Job Plans Tab | 82 | As a User, I want Search Functionality. | Implement Search Functionality | Working Search is implemented | High | 2 | 19 | Team Member 1
Job Detail Page - Job Plans Tab | 83 | As a User, I want Environment Status Display. | Implement Color-coded environment status indicators | Environment Status Indicators are implemented | High | 2 | 19 | Team Member 2
Job Detail Page - Run Statistics Tab | 84 | As a User, I want Dynamic Filters Section. | Implement filter bar with date pickers and environment dropdown | Filter Bar Component is implemented | High | 2 | 19 | Team Member 3
Job Detail Page - Run Statistics Tab | 85 | As a User, I want Apply/Reset Functionality. | Implement Apply and Reset buttons for filters | Apply/Reset Functionality is implemented | High | 2 | 20 | Team Member 1
Job Detail Page - Run Statistics Tab | 86 | As a User, I want Summary Tiles. | Display summary tiles for total runs, successful runs, failed runs, avg duration | Summary Tiles are displayed | High | 2 | 20 | Team Member 2
Job Detail Page - Run Statistics Tab | 87 | As a User, I want Search Functionality. | Implement search functionality for Job Plan, Duration, Status | Search Functionality is implemented | High | 2 | 20 | Team Member 3
Job Detail Page - Run Statistics Tab | 88 | As a User, I want Data Table. | Display job run data in tabular format | Run Statistics Table is displayed | High | 3 | 20 | Team Member 1
Job Detail Page - Run Statistics Tab | 89 | As a User, I want SLA-Based Duration Highlighting. | Highlight duration values based on SLA | SLA Highlighting is implemented | High | 3 | 21 | Team Member 2
Job Detail Page - Incidents Tab | 90 | As a User, I want Header Section. | Implement Summary tiles for Total, Last 7 Days, and This Month | Summary Tiles are implemented | High | 2 | 21 | Team Member 3
Job Detail Page - Incidents Tab | 91 | As a User, I want Filters Section. | Implement date pickers and environment dropdown filters | Filter Section is implemented | High | 2 | 21 | Team Member 1
Job Detail Page - Incidents Tab | 92 | As a User, I want Search Functionality. | Implement search functionality across columns | Search Functionality is implemented | High | 2 | 21 | Team Member 2
Job Detail Page - Incidents Tab | 93 | As a User, I want Data Table. | Display incident data in tabular format | Incident Data Table is displayed | High | 3 | 22 | Team Member 3
Job Detail Page - Incidents Tab | 94 | As a User, I want Incident Number Hyperlinking. | Implement hyperlink to ServiceNow incident page | Incident Number Hyperlink is implemented | High | 1 | 22 | Team Member 1
Job Detail Page - Incidents Tab | 95 | As a User, I want Status Badge UI Behavior. | Implement color-coded status badges | Status Badges are implemented | High | 2 | 22 | Team Member 2
Job Detail Page - Incidents Tab | 96 | As a User, I want Incident Details Popup Trigger. | Click on "Eye" icon to show Incident Details Popup | Popup Trigger is implemented | High | 1 | 22 | Team Member 3
Job Detail Page - Incidents Tab | 97 | As a User, I want Incident Details Popup. | Incident Details Popup Implementation | Incident Details Popup is implemented | High | 3 | 23 | Team Member 1
Job Detail Page - Change Requests Tab | 98 | As a User, I want Filters | Implement date range and environment filters | Change Request Filters are implemented | High | 2 | 23 | Team Member 2
Job Detail Page - Change Requests Tab | 99 | As a User, I want Search | Implement search functionality across relevant columns | Change Request Search is implemented | High | 2 | 23 | Team Member 3
Job Detail Page - Change Requests Tab | 100 | As a User, I want Data Table | Display change request data in tabular format | Change Request Table is displayed | High | 3 | 23 | Team Member 1
Job Detail Page - Change Requests Tab | 101 | As a User, I want Hyperlink Behavior | Implement hyperlink to Change Request on ServiceNow (if API available) | Change Request Hyperlink is implemented | High | 1 | 24 | Team Member 2
Job Detail Page - Change Requests Tab | 102 | As a User, I want Status Indicator | Functionality to color code Change Request status | Status Indicator on Change Request is implemented | High | 2 | 24 | Team Member 3
Job Plan Detail Page | 103 | As a User, I want Header Section | Implement Job Plan Title, Environment, Last Run Status, Last Modified Date | Header Section is implemented | High | 2 | 24 | Team Member 1
Job Plan Detail Page | 104 | As a User, I want Job Plan Overview | Implement Description | Job Plan Description is implemented | High | 3 | 24 | Team Member 2
Job Plan Detail Page | 105 | As a User, I want Tab Behavior | Implement Jobs Tab as Default | Jobs Tab as Default is implemented | High | 1 | 25 | Team Member 3
Job Plan Detail Page | 106 | As a User, I want Dynamic Tab Navigation | Implement Dynamic Tab Navigation | Dynamic Tab Navigation is implemented | High | 2 | 25 | Team Member 1
Job Plan Detail Page - Jobs Tab | 107 | As a User, I want Filter Section | Implement Filter Section with Environment Dropdown | Filter Section is implemented | High | 2 | 25 | Team Member 2
Job Plan Detail Page - Jobs Tab | 108 | As a User, I want Search Bar | Implement Search Bar with Job Name, Description | Search Bar is implemented | High | 2 | 25 | Team Member 3
Job Plan Detail Page - Jobs Tab | 109 | As a User, I want Job List Table | Implement Job List Table with required columns | Job List Table is implemented | High | 3 | 26 | Team Member 1
Job Plan Detail Page - Jobs Tab | 110 | As a User, I want Hyperlink Navigation | Job Name hyperlinks to Job Detail Page | Job Detail Page Hyperlink is implemented | High | 1 | 26 | Team Member 2
Job Plan Detail Page - Jobs Tab | 111 | As a User, I want Filtering | Environment dropdown filter updates Job List Table | Dynamic Filtered Job List is implemented | High | 2 | 26 | Team Member 3
Job Plan Detail Page - Jobs Tab | 112 | As a User, I want Search | Search functionality filters Job List Table by Job Name or Description | Dynamic Search Results are implemented | High | 2 | 26 | Team Member 1
Job Plan Detail Page - Jobs Tab | 113 | As a User, I want Sorting | Enable sorting on Job Name, Description and Last Modified Date | Sorting Functionality is implemented | High | 3 | 27 | Team Member 2
Job Plan Detail Page - Run Statistics Tab | 114 | As a User, I want Summary Section | Display Total Runs, Success Runs, Failed Runs and Avg. Duration | Summary Section is implemented | High | 2 | 27 | Team Member 3
Job Plan Detail Page - Run Statistics Tab | 115 | As a User, I want Filters Section | Implement Start Date/End Date and Environment filters | Date & Environment Filters are implemented | High | 2 | 27 | Team Member 1
Job Plan Detail Page - Run Statistics Tab | 116 | As a User, I want Search Bar | Implement Search Bar with Job Name, Job Plan, Type, Environment or Status | Search Functionality is implemented | High | 2 | 27 | Team Member 2
Job Plan Detail Page - Run Statistics Tab | 117 | As a User, I want Run Statistics Table | Display Job/Job Plan, Type, Planned Start Time, Actual Start Time, End Time, Duration, Environment, Status | Run Statistics Table is implemented | High | 3 | 28 | Team Member 3
Job Plan Detail Page - Run Statistics Tab | 118 | As a User, I want Dynamic Update | Dynamic data updates without Page Reload | Dynamic Data Loading is implemented | High | 3 | 28 | Team Member 1
Job Plan Detail Page - Run Statistics Tab | 119 | As a User, I want Sorting & Filtering | Functionality to Sort & Filter | Sorting & Filtering Functionality is implemented | High | 3 | 28 | Team Member 2
Job Plan Detail Page - Run Statistics Tab | 120 | As a User, I want Color Indicators | Display Color Indicators to show SLA Breach | SLA Breach Visualization is implemented | High | 3 | 28 | Team Member 3
Job Plan Detail Page - Incidents Tab | 121 | As a User, I want Summary Section | Display Total, Last 7 Day's and This Month Incidents | Incidents Summary Section is implemented | High | 2 | 29 | Team Member 1
Job Plan Detail Page - Incidents Tab | 122 | As a User, I want Filters | Start Date / End Date, Environment Filters implementation | Incidents Filters are implemented | High | 2 | 29 | Team Member 2
Job Plan Detail Page - Incidents Tab | 123 | As a User, I want Search Bar | Ability to search Incidents | Incidents Search is implemented | High | 2 | 29 | Team Member 3
Job Plan Detail Page - Incidents Tab | 124 | As a User, I want Incident Table | Functionality to display all Incidents | Incidents Table is implemented | High | 3 | 29 | Team Member 1
Job Plan Detail Page - Incidents Tab | 125 | As a User, I want Hyperlink Behavior | Functionality to link Incident to ServiceNow or Popup | Incidents Hyperlink Functionality is implemented | High | 1 | 30 | Team Member 2
Job Plan Detail Page - Incidents Tab | 126 | As a User, I want Status Indicator | Functionality to color code Incident status | Status Indicator on Incident is implemented | High | 2 | 30 | Team Member 3
Job Plan Detail Page - Incidents Tab | 127 | As a User, I want Incident Details Popup | Implement Incident Details Popup | Incident Details Popup is implemented | High | 3 | 30 | Team Member 1
Job Plan Detail Page - Incidents Tab | 128 | As a User, I want Status Badge UI Behavior | Implement Color-coded status badges | Status Badges are implemented | High | 2 | 30 | Team Member 2
Job Plan Detail Page - Change Request Tab | 129 | As a User, I want Summary Section | Implement Summary tiles for Total, Open, Closed Change Requests | Summary Tiles are implemented | High | 2 | 31 | Team Member 3
Job Plan Detail Page - Change Request Tab | 130 | As a User, I want Filters | Implement date range and environment filters | Change Request Filters are implemented | High | 2 | 31 | Team Member 1
Job Plan Detail Page - Change Request Tab | 131 | As a User, I want Search Bar | Ability to search Change Requests | Change Request Search is implemented | High | 2 | 31 | Team Member 2
Job Plan Detail Page - Change Request Tab | 132 | As a User, I want Change Request Table | Functionality to display all Change Request | Change Request Table is implemented | High | 3 | 31 | Team Member 3
Job Plan Detail Page - Change Request Tab | 133 | As a User, I want Hyperlink Behavior | Functionality to link Change Request to ServiceNow or Popup | Change Request Hyperlink Functionality is implemented | High | 1 | 32 | Team Member 1
Job Plan Detail Page - Change Request Tab | 134 | As a User, I want Status Indicator | Functionality to color code Change Request status | Status Indicator on Change Request is implemented | High | 2 | 32 | Team Member 2
Admin Module | 135 | As an administrator, I want to manage users so that I can control access to the system. | Develop UI for user management | User Management UI is created. | High | 3 | 32 | Team Member 3
Admin Module | 136 | As an administrator, I want to manage users so that I can control access to the system. | Implement backend logic for user management (create, edit, delete) | User Management Functionality is implemented. | High | 3 | 32 | Team Member 1
Admin Module | 137 | As an administrator, I want to manage roles so that I can control access to the system. | Develop UI for role management | Role Management UI is created. | High | 3 | 33 | Team Member 2
Admin Module | 138 | As an administrator, I want to manage roles so that I can control access to the system. | Implement backend logic for role management (create, edit, delete) | Role Management Functionality is implemented. | High | 3 | 33 | Team Member 3
Admin Module | 139 | As an administrator, I want to manage reports so that I can customize the reports. | Develop UI for report management | Report Management UI is created. | High | 3 | 33 | Team Member 1
Admin Module | 140 | As an administrator, I want to manage reports so that I can customize the reports. | Implement backend logic for report management | Report Management Functionality is implemented. | High | 3 | 33 | Team Member 2
Admin Module | 141 | As an administrator, I want to manage support so that I can track user issues. | Develop UI for support management | Support Management UI is created. | High | 3 | 34 | Team Member 3
Admin Module | 142 | As an administrator, I want to manage support so that I can track user issues. | Implement backend logic for support management | Support Management Functionality is implemented. | High | 3 | 34 | Team Member 1
Templates Module | 143 | As a support agent, I want templates with pre-defined Jobs, Job Plans, Change Requests, and Incidents | Implement the screen to create Templates | Screen for Template creation is implemented | High | 3 | 34 | Team Member 2
Templates Module | 144 | As a support agent, I want templates with pre-defined Jobs, Job Plans, Change Requests, and Incidents | Implement API's to be called in the front end for Template creation | API's to support the Template creation. are implemented | High | 3 | 34 | Team Member 3
Reporting | 145 | As a user, I want to see Power BI reports so that I can analyze data. | Embed Power BI reports in the application | Embedded Power BI Reports are displayed. | High | 2 | 35 | Team Member 1
Reporting | 146 | As a user, I want the Power BI data to be up-to-date so that I can see the latest information. | Configure data refresh schedule for Power BI reports | Power BI Data Refresh is configured. | High | 2 | 35 | Team Member 2
Testing | 147 | As a developer, I want to write unit tests so that I can ensure the code is working correctly. | Write and execute unit tests for all modules | Unit Test Results are documented. | High | 3 | 35 | Team Member 3
Testing | 148 | As a tester, I want to perform integration testing so that I can ensure the modules are working together correctly. | Perform integration testing between different modules | Integration Test Results are documented. | High | 3 | 35 | Team Member 1
Testing | 149 | As a user, I want to participate in user acceptance testing (UAT) so that I can ensure the application meets my needs. | Conduct UAT with end-users | UAT Sign-off is obtained. | High | 2 | 36 | Team Member 2
Deployment | 150 | As a release manager, I want to prepare a deployment package so that I can deploy the application. | Prepare Deployment Package | Deployment Package is created. | High | 2 | 36 | Team Member 3
Deployment | 151 | As a release manager, I want to deploy the application to the staging environment so that I can test it. | Deploy to Staging Environment | Staging Environment Deployment is successful. | High | 3 | 36 | Team Member 1
Deployment | 152 | As a tester, I want to conduct final testing on the staging environment so that I can ensure the application is ready for production. | Conduct Final Testing | Final Test Results are documented. | High | 3 | 37 | Team Member 2
Documentation | 153 | As a technical writer, I want to develop a user manual so that users can learn how to use the application. | Develop User Manual | User Manual is created. | High | 3 | 37 | Team Member 3
Documentation | 154 | As a technical writer, I want to develop API documentation so that developers can integrate with the application. | Develop API Documentation | API Documentation is created. | High | 3 | 37 | Team Member 1
Documentation | 155 | As a release manager, I want to create release notes so that users can see what has changed in each release. | Create Release Notes | Release Notes are created for each release. | High | 2 | 38 | Team Member 2
Training | 156 | As a trainer, I want to conduct user training sessions so that users can learn how to use the application. | Conduct User Training | Training Materials are used and trainees participate. | High | 3 | 38 | Team Member 3
Training | 157 | As a trainer, I want to prepare training materials so that users can learn how to use the application. | Prepare Training Materials | Trained Users successfully use training materials | High | 3 | 38 | Team Member 1
Project Closure | 158 | As a project manager, I want to conduct a final project review so that we can assess the project's success. | Final Project Review | Project Closure Report is created. | High | 2 | 39 | Team Member 2
Project Closure | 159 | As a project manager, I want to hand over all project documentation to the client so that they have all the information they need. | Documentation Handover | Handover Documentation is complete. | High | 2 | 39 | Team Member 3