## Sheet
Module Name | Tasks | Subtasks | Deliverables
Project Setup | Define Project Scope | Review FRD and identify key deliverables | Scope Document
Project Setup | Define Project Scope | Identify in-scope and out-of-scope functionalities | Scope Document
Project Setup | Define Project Scope | Obtain sign-off on scope from stakeholders | Approved Scope Document
Project Setup | Project Planning | Create a detailed project schedule | Project Schedule (Gantt Chart)
Project Setup | Project Planning | Assign tasks and responsibilities to team members | Responsibility Assignment Matrix
Project Setup | Project Planning | Establish communication and reporting protocols | Communication Plan
Project Setup | Set up Development Environment | Provision necessary hardware and software | Development Environment Setup
Project Setup | Set up Development Environment | Configure version control system (Git) | Git Repository
Project Setup | Set up Development Environment | Set up testing and staging environments | Testing and Staging Environments
Authentication & Authorization | Configure Okta Integration | Integrate Okta for single sign-on | Okta Integration Document
Authentication & Authorization | Configure Okta Integration | Test Okta authentication flow | Working Okta Authentication
Authentication & Authorization | Implement Role-Based Access Control (RBAC) | Define user roles and permissions (Admin, Developer, Read-Only, Support Engineer) | RBAC Matrix
Authentication & Authorization | Implement Role-Based Access Control (RBAC) | Implement RBAC logic in the application | RBAC Implementation
Authentication & Authorization | Implement Role-Based Access Control (RBAC) | Test user roles and permissions | Verified RBAC Implementation
Data Layer - Snowflake | Set up Snowflake Connection | Establish connection to Snowflake database | Snowflake Connection String
Data Layer - Snowflake | Data Model Implementation | Implement data model based on ERD provided | Data Model Schema
Data Layer - Snowflake | Data Extraction Scripts | Create scripts to extract necessary data from Snowflake | Data Extraction Scripts
Data Layer - Snowflake | Data Extraction Scripts | Test data extraction scripts | Verified Data Extraction Scripts
Data Layer - External APIs | ServiceNow API Integration | Obtain API access to ServiceNow for Incidents and Change Requests | ServiceNow API Credentials
Data Layer - External APIs | ServiceNow API Integration | Implement API calls to fetch Incidents and Change Requests | ServiceNow API Integration Code
Data Layer - External APIs | UC4 API Integration | Obtain API access to UC4 for job and job plan data | UC4 API Credentials
Data Layer - External APIs | UC4 API Integration | Implement API calls to fetch job and job plan data | UC4 API Integration Code
Data Layer - Data Transformation | Implement Data Transformation Logic | Transform data extracted from Snowflake and APIs into the required format | Data Transformation Scripts
Data Layer - Data Transformation | Implement Data Transformation Logic | Test data transformation logic | Verified Data Transformation Scripts
Home Module | Implement Search Job Functionality | Create UI for job search | Search UI Component
Home Module | Implement Search Job Functionality | Implement backend logic for job search | Working Job Search
Home Module | Implement Subject Area List | Create UI for subject area list | Subject Area List UI Component
Home Module | Implement Subject Area List | Fetch subject area data from database | Subject Area List Data
Home Module | Implement Recent Incidents | Create UI for recent incidents | Recent Incidents UI Component
Home Module | Implement Recent Incidents | Fetch recent incident data from database | Recent Incidents Data
Home Module | Implement Change Requests | Create UI for Change Requests | Change Requests UI Component
Home Module | Implement Change Requests | Fetch Change Request data from database | Change Request Data
Dashboard Module | Implement System Health Overview | Design and develop system health overview dashboard | System Health Overview Dashboard UI
Dashboard Module | Implement System Health Overview | Fetch and display system health metrics | System Health Metrics Data
Dashboard Module | Implement Alerts | Design and develop alerts section | Alerts UI Component
Dashboard Module | Implement Alerts | Implement logic for displaying alerts | Alerts Data
Dashboard Module | Implement Key Metrics | Design and develop key metrics section | Key Metrics UI Component
Dashboard Module | Implement Key Metrics | Fetch and display key metrics data | Key Metrics Data
Job Scheduler Module | Implement Job Scheduler Screen | Design the Job Scheduler screen layout | Job Scheduler Screen Mockup
Job Scheduler Module | Implement Job Scheduler Screen | Develop the Job Scheduler screen UI | Job Scheduler UI Component
Job Scheduler Module | Implement Filter Bar Functionality | Develop Date Range Picker | Date Range Picker Component
Job Scheduler Module | Implement Filter Bar Functionality | Develop Environment Dropdown | Environment Dropdown Component
Job Scheduler Module | Implement Filter Bar Functionality | Implement Apply and Reset Buttons functionality | Working Apply/Reset Buttons
Job Scheduler Module | Implement Search Functionality | Develop Global Search Bar | Global Search Bar Component
Job Scheduler Module | Implement Search Functionality | Develop Job List Search | Job List Search Functionality
Job Scheduler Module | Implement Job Listing Table | Implement Pagination | Pagination Component
Job Scheduler Module | Implement Job Listing Table | Implement Sorting | Sorting Functionality
Job Scheduler Module | Implement Job Listing Table | Display Columns (Job Name, Job Plan, Job Type, Description, Environment, Last Run) | Job Listing Table with Required Columns
Job Scheduler Module | Implement Hyperlink Behavior | Implement Job Name Hyperlink to Job Detail Page | Job Name Hyperlink
Job Scheduler Module | Implement Hyperlink Behavior | Implement Job Plan Hyperlink to Job Plan Detail Page | Job Plan Hyperlink
Job Scheduler Module | Implement UI/UX Requirements | Implement Description field wrapping and truncation | Description Field Wrapping
Job Scheduler Module | Implement UI/UX Requirements | Implement Responsive Layout | Responsive Layout Implementation
Job Scheduler Module | Implement Backend Filtering | Optimize backend filtering for performance | Optimized Backend Filtering
Job Scheduler Module | Implement API Queries | Implement API queries with filter, sort, and pagination parameters | Working API Queries
Job Scheduler Module | Implement Security and Access Control | Ensure authorized users can view job data | Secure Job Data Access
Job Detail Page Module | Implement Header Section | Display full technical job name as page title | Page Title
Job Detail Page Module | Implement Job Metadata Section | Display Job Name, Job Type, Environment, Workflow, Last Run Status | Job Metadata Section
Job Detail Page Module | Implement Description Section | Display job's functionality and schedule details | Description Section
Job Detail Page Module | Implement Tabs Section | Implement tabs for Support Instructions, Job Plans, Run Stats, Incidents, Change Request | Tabbed Navigation
Job Detail Page Module | Implement Default Tab Load | Set Support Instructions as default tab | Default Tab Loading
Job Detail Page Module | Implement Dynamic Content Loading | Ensure each tab loads its data dynamically | Dynamic Content Loading
Job Detail Page Module | Implement Hyperlink Behavior | Implement Workflow field hyperlink | Workflow Hyperlink
Job Detail Page Module | Implement Hyperlink Behavior | Implement Document hyperlinks | Document Hyperlinks
Job Detail Page Module | Implement UI/UX Requirements | Implement card-based layout, environment labels, word wrapping | UI/UX Improvements
Job Detail Page - Support Instructions | Implement SLA Display | Display SLA in top-right corner | SLA Display
Job Detail Page - Support Instructions | Implement Restart Instructions | Display restart steps as multi-line paragraph | Restart Instructions
Job Detail Page - Support Instructions | Implement Input Details | Display input details as bullet points or comma-separated list | Input Details
Job Detail Page - Support Instructions | Implement Output Details | Display output details including locations/destinations | Output Details
Job Detail Page - Support Instructions | Implement Support Notes | Display support notes and guidelines | Support Notes
Job Detail Page - Support Instructions | Implement Exceptions for Non-Production Environments | Display environment-specific instructions | Non-Production Exceptions
Job Detail Page - Support Instructions | Implement Schedule Frequency | Display the job schedule frequency | Schedule Frequency
Job Detail Page - Support Instructions | Implement Linked Support Document | Display and link the support document | Linked Support Document
Job Detail Page - Support Instructions | Implement Secured Access to Linked Documents | Ensure secure access to PDF | Secured Document Access
Job Detail Page - Job Plans Tab | Implement Header Section | Implement Tabs Navigation | Tab Navigation
Job Detail Page - Job Plans Tab | Implement Header Section | Implement Search Field | Search Field
Job Detail Page - Job Plans Tab | Implement Job Plan Table | Display Job Plan, Description, Environment, Last Modified Date columns | Job Plan Table
Job Detail Page - Job Plans Tab | Implement Pagination | Implement Pagination | Pagination Controls
Job Detail Page - Job Plans Tab | Implement Environment Filter | Implement Environment Filter | Environment Filter
Job Detail Page - Job Plans Tab | Implement Dynamic Content Loading | Dynamically load job plans based on filters | Dynamic Job Plans Loading
Job Detail Page - Job Plans Tab | Implement Sorting | Implement Sorting | Sorting Functionality
Job Detail Page - Job Plans Tab | Implement Hyperlink Behavior | Implement hyperlink on Job Plan name | Job Plan Hyperlink
Job Detail Page - Job Plans Tab | Implement Search Functionality | Implement Search Functionality | Working Search
Job Detail Page - Job Plans Tab | Implement Environment Status Display | Implement Color-coded environment status indicators | Environment Status Indicators
Job Detail Page - Run Statistics Tab | Implement Dynamic Filters Section | Implement filter bar with date pickers and environment dropdown | Filter Bar Component
Job Detail Page - Run Statistics Tab | Implement Apply/Reset Functionality | Implement Apply and Reset buttons for filters | Apply/Reset Functionality
Job Detail Page - Run Statistics Tab | Implement Summary Tiles | Display summary tiles for total runs, successful runs, failed runs, avg duration | Summary Tiles
Job Detail Page - Run Statistics Tab | Implement Search Functionality | Implement search functionality for Job Plan, Duration, Status | Search Functionality
Job Detail Page - Run Statistics Tab | Implement Data Table | Display job run data in tabular format | Run Statistics Table
Job Detail Page - Run Statistics Tab | Implement SLA-Based Duration Highlighting | Highlight duration values based on SLA | SLA Highlighting
Job Detail Page - Incidents Tab | Implement Header Section | Implement Summary tiles for Total, Last 7 Days, and This Month | Summary Tiles
Job Detail Page - Incidents Tab | Implement Filters Section | Implement date pickers and environment dropdown filters | Filter Section
Job Detail Page - Incidents Tab | Implement Search Functionality | Implement search functionality across columns | Search Functionality
Job Detail Page - Incidents Tab | Implement Data Table | Display incident data in tabular format | Incident Data Table
Job Detail Page - Incidents Tab | Implement Incident Number Hyperlinking | Implement hyperlink to ServiceNow incident page | Incident Number Hyperlink
Job Detail Page - Incidents Tab | Implement Status Badge UI Behavior | Implement color-coded status badges | Status Badges
Job Detail Page - Incidents Tab | Incident Details Popup Trigger | Click on "Eye" icon to show Incident Details Popup | Popup Trigger
Job Detail Page - Incidents Tab | Implement Incident Details Popup | Incident Details Popup Implementation | Incident Details Popup
Job Detail Page - Change Requests Tab | Implement Filters | Implement date range and environment filters | Change Request Filters
Job Detail Page - Change Requests Tab | Implement Search | Implement search functionality across relevant columns | Change Request Search
Job Detail Page - Change Requests Tab | Implement Data Table | Display change request data in tabular format | Change Request Table
Job Detail Page - Change Requests Tab | Implement Hyperlink Behavior | Implement hyperlink to Change Request on ServiceNow (if API available) | Change Request Hyperlink
Job Plan Detail Page | Implement Header Section | Implement Job Plan Title, Environment, Last Run Status, Last Modified Date | Header Section
Job Plan Detail Page | Implement Job Plan Overview | Implement Description | Job Plan Description
Job Plan Detail Page | Implement Tab Behavior | Implement Jobs Tab as Default | Jobs Tab as Default
Job Plan Detail Page | Implement Dynamic Tab Navigation | Implement Dynamic Tab Navigation | Dynamic Tab Navigation
Job Plan Detail Page - Jobs Tab | Implement Filter Section | Implement Filter Section with Environment Dropdown | Filter Section
Job Plan Detail Page - Jobs Tab | Implement Search Bar | Implement Search Bar with Job Name, Description | Search Bar
Job Plan Detail Page - Jobs Tab | Implement Job List Table | Implement Job List Table with required columns | Job List Table
Job Plan Detail Page - Jobs Tab | Implement Hyperlink Navigation | Job Name hyperlinks to Job Detail Page | Job Detail Page Hyperlink
Job Plan Detail Page - Jobs Tab | Implement Filtering | Environment dropdown filter updates Job List Table | Dynamic Filtered Job List
Job Plan Detail Page - Jobs Tab | Implement Search | Search functionality filters Job List Table by Job Name or Description | Dynamic Search Results
Job Plan Detail Page - Jobs Tab | Implement Sorting | Enable sorting on Job Name, Description and Last Modified Date | Sorting Functionality
Job Plan Detail Page - Run Statistics Tab | Implement Summary Section | Display Total Runs, Success Runs, Failed Runs and Avg. Duration | Summary Section
Job Plan Detail Page - Run Statistics Tab | Implement Filters Section | Implement Start Date/End Date and Environment filters | Date & Environment Filters
Job Plan Detail Page - Run Statistics Tab | Implement Search Bar | Implement Search Bar with Job Name, Job Plan, Type, Environment or Status | Search Functionality
Job Plan Detail Page - Run Statistics Tab | Implement Run Statistics Table | Display Job/Job Plan, Type, Planned Start Time, Actual Start Time, End Time, Duration, Environment, Status | Run Statistics Table
Job Plan Detail Page - Run Statistics Tab | Implement Dynamic Update | Dynamic data updates without Page Reload | Dynamic Data Loading
Job Plan Detail Page - Run Statistics Tab | Implement Sorting & Filtering | Functionality to Sort & Filter | Sorting & Filtering Functionality
Job Plan Detail Page - Run Statistics Tab | Implement Color Indicators | Display Color Indicators to show SLA Breach | SLA Breach Visualization
Job Plan Detail Page - Incidents Tab | Implement Summary Section | Display Total, Last 7 Day's and This Month Incidents | Incidents Summary Section
Job Plan Detail Page - Incidents Tab | Implement Filters | Start Date / End Date, Environment Filters implementation | Incidents Filters
Job Plan Detail Page - Incidents Tab | Implement Search Bar | Ability to search Incidents | Incidents Search
Job Plan Detail Page - Incidents Tab | Implement Incident Table | Functionality to display all Incidents | Incidents Table
Job Plan Detail Page - Incidents Tab | Implement Hyperlink Behavior | Functionality to link Incident to ServiceNow or Popup | Incidents Hyperlink Functionality
Job Plan Detail Page - Incidents Tab | Implement Status Indicator | Functionality to color code Incident status | Status Indicator on Incident
Job Plan Detail Page - Incidents Tab | Implement Incident Details Popup | Implement Incident Details Popup | Incident Details Popup
Job Plan Detail Page - Incidents Tab | Implement Status Badge UI Behavior | Implement Color-coded status badges | Status Badges
Job Plan Detail Page - Change Request Tab | Implement Summary Section | Implement Summary tiles for Total, Open, Closed Change Requests | Summary Tiles
Job Plan Detail Page - Change Request Tab | Implement Filters | Implement date range and environment filters | Change Request Filters
Job Plan Detail Page - Change Request Tab | Implement Search Bar | Ability to search Change Requests | Change Request Search
Job Plan Detail Page - Change Request Tab | Implement Change Request Table | Functionality to display all Change Request | Change Request Table
Job Plan Detail Page - Change Request Tab | Implement Hyperlink Behavior | Functionality to link Change Request to ServiceNow or Popup | Change Request Hyperlink Functionality
Job Plan Detail Page - Change Request Tab | Implement Status Indicator | Functionality to color code Change Request status | Status Indicator on Change Request
Admin Module | Implement User Management | Develop UI for user management | User Management UI
Admin Module | Implement User Management | Implement backend logic for user management (create, edit, delete) | User Management Functionality
Admin Module | Implement Role Management | Develop UI for role management | Role Management UI
Admin Module | Implement Role Management | Implement backend logic for role management (create, edit, delete) | Role Management Functionality
Admin Module | Implement Report Management | Develop UI for report management | Report Management UI
Admin Module | Implement Report Management | Implement backend logic for report management | Report Management Functionality
Admin Module | Implement Support Management | Develop UI for support management | Support Management UI
Admin Module | Implement Support Management | Implement backend logic for support management | Support Management Functionality
Templates Module | Implement templates with pre-defined Jobs, Job Plans, Change Requests, and Incidents | Implement the screen to create Templates | Screen for Template creation
Templates Module | Implement templates with pre-defined Jobs, Job Plans, Change Requests, and Incidents | Implement API's to be called in the front end for Template creation | API's to support the Template creation.
Reporting | Embed Power BI Reports | Embed Power BI reports in the application | Embedded Power BI Reports
Reporting | Configure Data Refresh | Configure data refresh schedule for Power BI reports | Power BI Data Refresh
Testing | Unit Testing | Write and execute unit tests for all modules | Unit Test Results
Testing | Integration Testing | Perform integration testing between different modules | Integration Test Results
Testing | User Acceptance Testing (UAT) | Conduct UAT with end-users | UAT Sign-off
Deployment | Prepare Deployment Package | Create a deployment package with all necessary components | Deployment Package
Deployment | Deploy to Staging Environment | Deploy the application to the staging environment | Staging Environment Deployment
Deployment | Conduct Final Testing | Conduct final testing on the staging environment | Final Test Results
Documentation | Develop User Manual | Create a user manual for the application | User Manual
Documentation | Develop API Documentation | Create API documentation for all implemented APIs | API Documentation
Documentation | Create Release Notes | Create release notes for each release | Release Notes
Training | Conduct User Training | Conduct user training sessions | Training Materials
Training | Prepare Training Materials | Create training materials for the application | Trained Users
Project Closure | Final Project Review | Conduct a final project review with stakeholders | Project Closure Report
Project Closure | Documentation Handover | Hand over all project documentation to the client | Handover Documentation