## Sheet
Epic | ID | User Story | Tasks/Subtasks | Acceptance Criteria | Priority | Story Points | Sprint Number | Assignee
Project Initialization | 1 | As a project manager, I need to define the project scope to understand the boundaries and objectives. | Define Project Scope | Project Scope Document is created. | High | 3 | 1 | Team Member 1
Project Initialization | 2 | As a project manager, I need to define the project scope to understand the boundaries and objectives. | Identify out-of-scope items | List of Out-of-Scope Items is created. | High | 2 | 1 | Team Member 2
Project Initialization | 3 | As a project manager, I need to define the project scope to understand the boundaries and objectives. | Document assumptions and dependencies | Assumptions and Dependencies Document is created. | High | 2 | 1 | Team Member 3
Project Initialization | 4 | As a project manager, I need to define the project timeline to ensure timely completion. | Estimate task durations | Project Timeline (Gantt Chart) is created. | High | 3 | 1 | Team Member 1
Project Initialization | 5 | As a project manager, I need to define the project timeline to ensure timely completion. | Identify critical path | Critical Path Analysis Document is created. | High | 2 | 1 | Team Member 2
Project Initialization | 6 | As a developer, I need to setup the development environment to start working on the project. | Install necessary software (JDK, IDE) | Installed Development Environment is available. | High | 3 | 2 | Team Member 3
Project Initialization | 7 | As a developer, I need to setup the development environment to start working on the project. | Configure version control (Git) | Git Repository Configured and accessible. | High | 2 | 2 | Team Member 1
Project Initialization | 8 | As a developer, I need to setup the development environment to start working on the project. | Setup project structure | Project Directory Structure Created and organized. | High | 2 | 2 | Team Member 2
UI Development | 9 | As a user, I want a collapsible sidebar menu so I can easily navigate the application. | Design collapsible sidebar | Sidebar Design Mockup is approved. | High | 5 | 2 | Team Member 3
UI Development | 10 | As a user, I want the menu items to be visible based on my role so I only see what's relevant to me. | Implement role-based visibility | Role-Based Menu Visibility Implemented and tested. | High | 3 | 2 | Team Member 1
UI Development | 11 | As a user, I want the active menu item to be highlighted so I know where I am in the application. | Implement menu item highlighting | Active Menu Item Highlighting is functional. | Medium | 2 | 3 | Team Member 2
UI Development | 12 | As a user, I want to be able to search for jobs on the home page. | Implement Search Job feature | Search Job Functionality Working and returns relevant results. | High | 5 | 3 | Team Member 3
UI Development | 13 | As a user, I want to see a list of subject areas on the home page. | Implement Subject Area List | Subject Area List Displayed correctly. | Medium | 3 | 3 | Team Member 1
UI Development | 14 | As a user, I want to see recent incidents displayed on the home page. | Display Recent Incidents | Recent Incidents Displayed on Home Page. | Medium | 2 | 3 | Team Member 2
UI Development | 15 | As a user, I want to see change requests displayed on the home page. | Display Change Requests | Change Requests Displayed on Home Page. | Medium | 2 | 4 | Team Member 3
UI Development | 16 | As a user, I want to see Rally tickets displayed on the home page. | Display Rally Tickets | Rally Tickets Displayed on Home Page. | Medium | 2 | 4 | Team Member 1
UI Development | 17 | As a user, I want to see job information displayed on the Job Detail page. | Implement Job Information Section | Job Information Section Implemented with correct data. | High | 5 | 4 | Team Member 2
UI Development | 18 | As a user, I want to see job support instructions displayed on the Job Detail page. | Implement Job Support Instructions Section | Job Support Instructions Section Implemented and accurate. | Medium | 3 | 4 | Team Member 3
UI Development | 19 | As a user, I want to see error logs displayed on the Job Detail page. | Implement Error Logs Section | Error Logs Section Implemented and displaying relevant logs. | Medium | 3 | 5 | Team Member 1
UI Development | 20 | As a user, I want to see associated incidents displayed on the Job Detail page. | Implement Associated Incidents Section | Associated Incidents Section Implemented and linked to incidents. | Medium | 2 | 5 | Team Member 2
UI Development | 21 | As a user, I want to see change requests displayed on the Job Detail page. | Implement Change Requests Section | Change Requests Section Implemented and linked to change requests. | Medium | 2 | 5 | Team Member 3
UI Development | 22 | As a user, I want to see the job schedule displayed on the Job Detail page. | Implement Job Schedule Section | Job Schedule Section Implemented with correct schedule data. | Medium | 3 | 5 | Team Member 1
UI Development | 23 | As a user, I want to see job run statistics displayed on the Job Detail page. | Implement Job Run Stats Section | Job Run Stats Section Implemented with accurate statistics. | Medium | 3 | 6 | Team Member 2
UI Development | 24 | As a user, I want a system health overview on the dashboard. | Design System Health Overview | System Health Overview Design is approved. | High | 3 | 6 | Team Member 3
UI Development | 25 | As a user, I want to see system health metrics displayed on the dashboard. | Implement System Health Metrics | System Health Metrics Displayed and updated regularly. | High | 5 | 6 | Team Member 1
UI Development | 26 | As a user, I want an alerting system to notify me of issues. | Implement Alerting System | Alerting System Functional and sends notifications. | High | 4 | 6 | Team Member 2
UI Development | 27 | As a user, I want to see a list of subject areas in the Subject Area Management module. | Implement Subject Area List View | Subject Area List View Developed and displays subject areas. | Medium | 3 | 7 | Team Member 3
UI Development | 28 | As a user, I want to be able to add new subject areas in the Subject Area Management module. | Implement Add Subject Area Functionality | Add Subject Area Functionality Working and saves new subject areas. | Medium | 4 | 7 | Team Member 1
UI Development | 29 | As a user, I want to be able to edit existing subject areas in the Subject Area Management module. | Implement Edit Subject Area Functionality | Edit Subject Area Functionality Working and updates subject areas. | Medium | 4 | 7 | Team Member 2
UI Development | 30 | As a user, I want to be able to delete subject areas in the Subject Area Management module. | Implement Delete Subject Area Functionality | Delete Subject Area Functionality Working and removes subject areas. | Medium | 3 | 7 | Team Member 3
UI Development | 31 | As a user, I want to see a list of jobs in the Jobs List module. | Implement Job Listing View | Job Listing View Developed and displays jobs. | Medium | 3 | 8 | Team Member 1
UI Development | 32 | As a user, I want to be able to filter jobs in the Jobs List module. | Implement Filtering Functionality | Job Filtering Functionality Working and filters jobs based on criteria. | Medium | 4 | 8 | Team Member 2
UI Development | 33 | As a user, I want to be able to sort jobs in the Jobs List module. | Implement Sorting Functionality | Job Sorting Functionality Working and sorts jobs based on selected column. | Medium | 3 | 8 | Team Member 3
UI Development | 34 | As a user, I want to be able to search for jobs in the Jobs List module. | Implement Search Functionality | Job Search Functionality Working and returns relevant jobs. | Medium | 3 | 8 | Team Member 1
UI Development | 35 | As a user, I want to see a list of change requests in the Change Requests module. | Implement Change Request List View | Change Request List View Developed and displays change requests. | Medium | 3 | 9 | Team Member 2
UI Development | 36 | As a user, I want to be able to view the details of a change request. | Implement View Change Request Details | Change Request Details View Developed and displays change request details. | Medium | 3 | 9 | Team Member 3
UI Development | 37 | As a user, I want to be able to manage change requests (approve, reject, etc.). | Implement Manage Change Requests | Change Request Management Functionality Working. | Medium | 4 | 9 | Team Member 1
UI Development | 38 | As a user, I want to see a list of incidents in the ServiceNow module. | Implement Incident List View | Incident List View Developed and displays incidents. | Medium | 3 | 9 | Team Member 2
UI Development | 39 | As a user, I want to be able to view the details of an incident. | Implement Incident Details View | Incident Details View Developed and displays incident details. | Medium | 3 | 10 | Team Member 3
UI Development | 40 | As a user, I want to be able to view Power BI reports. | Embed Power BI Reports | Embedded Power BI Reports Functional. | Medium | 3 | 10 | Team Member 1
UI Development | 41 | As an administrator, I want to be able to manage users. | Implement User Management | User Management Functionality Working (add, edit, delete). | Medium | 4 | 10 | Team Member 2
UI Development | 42 | As an administrator, I want to be able to manage roles. | Implement Role Management | Role Management Functionality Working (create, assign, edit). | Medium | 4 | 10 | Team Member 3
UI Development | 43 | As an administrator, I want to be able to manage reports. | Implement Report Management | Report Management Functionality Working (schedule, permissions). | Medium | 3 | 11 | Team Member 1
UI Development | 44 | As an administrator, I want to be able to manage support templates. | Implement Support Templates | Support Templates Functionality Working (create, edit, use). | Medium | 3 | 11 | Team Member 2
Backend Development | 45 | As a developer, I need to integrate with UC4 to fetch job data. | Develop API client to fetch job data from UC4 | UC4 API Client is created and connects to UC4. | High | 5 | 11 | Team Member 3
Backend Development | 46 | As a developer, I need to integrate with UC4 to fetch job data. | Implement data transformation logic | Transformed UC4 Data is in the correct format. | High | 3 | 11 | Team Member 1
Backend Development | 47 | As a developer, I need to integrate with ServiceNow to fetch incident data. | Develop API client to fetch incident data from ServiceNow | ServiceNow API Client is created and connects to ServiceNow. | High | 5 | 12 | Team Member 2
Backend Development | 48 | As a developer, I need to integrate with ServiceNow to fetch incident data. | Implement data transformation logic | Transformed ServiceNow Data is in the correct format. | High | 3 | 12 | Team Member 3
Backend Development | 49 | As a developer, I need to integrate with Informatica to fetch run statistics. | Develop API client to fetch run statistics from Informatica | Informatica API Client is created and connects to Informatica. | High | 5 | 12 | Team Member 1
Backend Development | 50 | As a developer, I need to integrate with Informatica to fetch run statistics. | Implement data transformation logic | Transformed Informatica Data is in the correct format. | High | 3 | 12 | Team Member 2
Backend Development | 51 | As a developer, I need to integrate with Rally to fetch ticket data. | Develop API client to fetch ticket data from Rally | Rally API Client is created and connects to Rally. | High | 5 | 13 | Team Member 3
Backend Development | 52 | As a developer, I need to integrate with Rally to fetch ticket data. | Implement data transformation logic | Transformed Rally Data is in the correct format. | High | 3 | 13 | Team Member 1
Backend Development | 53 | As a developer, I need to create API endpoints for the UI to access job data. | Create REST endpoints for job data | Job Data API Endpoints are created and functional. | High | 4 | 13 | Team Member 2
Backend Development | 54 | As a developer, I need to create API endpoints for the UI to access incident data. | Create REST endpoints for incident data | Incident Data API Endpoints are created and functional. | High | 4 | 13 | Team Member 3
Backend Development | 55 | As a developer, I need to create API endpoints for the UI to access run statistics. | Create REST endpoints for run statistics | Run Statistics API Endpoints are created and functional. | High | 4 | 14 | Team Member 1
Backend Development | 56 | As a developer, I need to create API endpoints for the UI to access Rally tickets. | Create REST endpoints for Rally tickets | Rally Ticket API Endpoints are created and functional. | High | 4 | 14 | Team Member 2
Backend Development | 57 | As a developer, I need to integrate with Okta to secure the application (Option 1). | Integrate with Okta (Option 1) | Okta Integration Implemented (Option 1) and tested. | High | 5 | 14 | Team Member 3
Backend Development | 58 | As a developer, I need to secure the REST APIs. | Secure REST APIs | Secured REST APIs are protected against unauthorized access. | High | 3 | 14 | Team Member 1
Backend Development | 59 | As a developer, I need to implement role-based access control. | Implement Role-Based Access Control | Role-Based Access Control Implemented and tested. | High | 3 | 15 | Team Member 2
Database Development | 60 | As a database administrator, I need to design the database schema. | Design Database Schema | Database Schema Design is complete and approved. | High | 5 | 15 | Team Member 3
Database Development | 61 | As a database administrator, I need to define the relationships between tables. | Define relationships between tables | Database Relationship Diagram is created and accurate. | High | 3 | 15 | Team Member 1
Database Development | 62 | As a database administrator, I need to implement a batch data refresh mechanism. | Implement Data Refresh | Batch Data Refresh Mechanism is implemented and runs successfully. | High | 5 | 15 | Team Member 2
Database Development | 63 | As a database administrator, I need to implement near real-time data refresh from Snowflake. | Implement Data Refresh | Near Real-Time Data Refresh Mechanism is implemented and functional. | High | 5 | 16 | Team Member 3
Testing | 64 | As a tester, I need to write unit tests for the backend APIs. | Unit Testing | Unit Test Cases and Results are documented and pass. | High | 5 | 16 | Team Member 1
Testing | 65 | As a tester, I need to test the integration between the UI and the backend. | Integration Testing | Integration Test Cases and Results are documented and pass. | High | 5 | 16 | Team Member 2
Testing | 66 | As a tester, I need to conduct user acceptance testing with DEMO-CLIENT users. | User Acceptance Testing (UAT) | UAT Test Cases and Results are documented and approved by DEMO-CLIENT. | High | 5 | 16 | Team Member 3
Testing | 67 | As a tester, I need to test the system performance under load. | Performance Testing | Performance Test Report is created and meets performance criteria. | High | 5 | 17 | Team Member 1
Okta Integration (Option 1) | 68 | As a frontend developer, I need to setup Client ID and Issuer URL in Vue.js. | Frontend Configuration | Client ID and Issuer URL Configured correctly. | Medium | 2 | 17 | Team Member 2
Okta Integration (Option 1) | 69 | As a frontend developer, I need to add Okta Vue and Okta SDK dependencies. | Frontend Configuration | Okta Dependencies Added and verified. | Medium | 2 | 17 | Team Member 3
Okta Integration (Option 1) | 70 | As a frontend developer, I need to implement Okta login page redirection. | Frontend Configuration | Login Page Redirection Implemented and redirects to Okta login. | Medium | 3 | 17 | Team Member 1
Okta Integration (Option 1) | 71 | As a frontend developer, I need to handle login requests and token storage. | Frontend Configuration | Token Storage Implementation stores tokens securely. | Medium | 4 | 18 | Team Member 2
Okta Integration (Option 1) | 72 | As a frontend developer, I need to implement role-based content control. | Frontend Configuration | Role-Based Content Control Implemented and displays content based on user roles. | Medium | 3 | 18 | Team Member 3
Okta Integration (Option 1) | 73 | As a frontend developer, I need to include the access token in API headers. | Frontend Configuration | Access Token Included in Headers for all API requests. | Medium | 2 | 18 | Team Member 1
Okta Integration (Option 1) | 74 | As a backend developer, I need to secure all REST APIs. | Backend Configuration | REST APIs Secured with Okta authentication. | High | 3 | 18 | Team Member 2
Okta Integration (Option 1) | 75 | As a backend developer, I need to create a security configuration class. | Backend Configuration | Security Configuration Class Created and configured for Okta. | Medium | 2 | 19 | Team Member 3
Okta Integration (Option 1) | 76 | As a backend developer, I need to validate the access token. | Backend Configuration | Access Token Validation Implemented and validates tokens against Okta. | High | 3 | 19 | Team Member 1
Okta Integration (Option 1) | 77 | As a backend developer, I need to create an API to retrieve user information (optional). | Backend Configuration | User Information API is created and returns user details. | Low | 2 | 19 | Team Member 2
Okta Integration (Option 1) | 78 | As an Okta administrator, I need to create an Okta demo account. | Okta Configuration | Okta Account Created for testing. | High | 1 | 19 | Team Member 3
Okta Integration (Option 1) | 79 | As an Okta administrator, I need to obtain the Issuer URI and Client ID. | Okta Configuration | Issuer URI and Client ID Obtained from Okta. | High | 1 | 20 | Team Member 1
Okta Integration (Option 1) | 80 | As an Okta administrator, I need to set roles and user info in Okta claims. | Okta Configuration | Okta Claims Configured with user roles and information. | High | 2 | 20 | Team Member 2
Okta Integration (Option 2) | 81 | As a backend developer, I need to open Okta login page from backend. | Backend Configuration | Login Page Redirection Implemented | Medium | 3 | 20 | Team Member 3
Okta Integration (Option 2) | 82 | As a backend developer, I need to set redirect and logout URLs. | Backend Configuration | Redirect and Logout URLs Configured | Medium | 2 | 20 | Team Member 1
Okta Integration (Option 2) | 83 | As a backend developer, I need to authenticate user and manage session. | Backend Configuration | Session Management Implemented | Medium | 3 | 20 | Team Member 2
Okta Integration (Option 2) | 84 | As a backend developer, I need to protect routes using Spring Security. | Backend Configuration | Routes Secured with Spring Security | Medium | 3 | 1 | Team Member 3
Okta Integration (Option 2) | 85 | As a backend developer, I need to Provide user info endpoint. | Backend Configuration | User Information Endpoint Created | Medium | 2 | 1 | Team Member 1
Okta Integration (Option 2) | 86 | As a backend developer, I need to provide token endpoint (optional). | Backend Configuration | Token Endpoint Created | Low | 2 | 1 | Team Member 2
Okta Integration (Option 2) | 87 | As a backend developer, I need to Implement logout functionality. | Backend Configuration | Logout Functionality Implemented | Medium | 2 | 1 | Team Member 3
Okta Integration (Option 2) | 88 | As an Okta administrator, I need to create an Okta demo account. | Okta Configuration | Okta Account Created | High | 1 | 2 | Team Member 1
Okta Integration (Option 2) | 89 | As an Okta administrator, I need to obtain the Issuer URI and Client ID. | Okta Configuration | Issuer URI and Client ID Obtained | High | 1 | 2 | Team Member 2
Okta Integration (Option 2) | 90 | As an Okta administrator, I need to set roles and user info in Okta claims. | Okta Configuration | Okta Claims Configured | High | 2 | 2 | Team Member 3
Documentation | 91 | As a technical writer, I need to create a user manual for the application. | Create User Manual | User Manual Document is complete and user-friendly. | Medium | 3 | 2 | Team Member 1
Documentation | 92 | As a technical writer, I need to create developer documentation for the application. | Create Developer Documentation | Developer Documentation is complete and covers API endpoints, database schema, and code architecture. | Medium | 5 | 3 | Team Member 2
Documentation | 93 | As a technical writer, I need to create a deployment guide for the application. | Create Deployment Guide | Deployment Guide is complete and provides step-by-step instructions. | Medium | 3 | 3 | Team Member 3
Project Management | 94 | As a project manager, I need to conduct weekly status meetings with stakeholders. | Weekly Status Meetings | Meeting Minutes are documented and distributed. | Low | 2 | 3 | Team Member 1
Project Management | 95 | As a project manager, I need to identify and mitigate project risks. | Risk Management | Risk Register is created and maintained. | High | 3 | 4 | Team Member 2
Deployment | 96 | As a DevOps engineer, I need to prepare the deployment package. | Prepare Deployment Package | Deployment Package is created and ready for deployment. | High | 3 | 4 | Team Member 3
Deployment | 97 | As a DevOps engineer, I need to create detailed deployment instructions. | Create Deployment Instructions | Deployment Instructions are detailed and step-by-step. | High | 3 | 4 | Team Member 1
Training | 98 | As a trainer, I need to prepare training materials for the users. | Prepare Training Materials | Training Materials are created (videos, documents). | Medium | 3 | 5 | Team Member 2
Training | 99 | As a trainer, I need to conduct training sessions for the users. | Conduct Training Sessions | Training Sessions Completed and users are trained on the application functionalities. | Medium | 3 | 5 | Team Member 3