## Sheet
```csv
Epic | ID | User Story | Tasks/Subtasks | Acceptance Criteria | Priority | Story Points | Sprint Number | Assignee
Project Initialization | PI-1 | As a project manager, I want to define the project scope so that the team understands the project boundaries. | Define Project Scope | Project Scope Document created and approved by stakeholders. | High | 3 | 1 | Team Member 1
Project Initialization | PI-2 | As a business analyst, I want to gather and document the project requirements so that the development team can build the right features. | Gather Requirements | Functional Requirements Document (FRD) created and reviewed by stakeholders. | High | 5 | 1 | Team Member 2
Project Initialization | PI-3 | As a developer, I want to set up a code repository so that the team can collaborate effectively. | Set up Repository | Git Repository initialized and accessible to all team members. | High | 2 | 1 | Team Member 3
Project Initialization | PI-4 | As a project manager, I want to establish a communication plan so that the team and stakeholders are informed throughout the project. | Establish Project Communication | Communication Plan created, documented, and communicated to all stakeholders. | Medium | 3 | 1 | Team Member 4
UI Design | UI-1 | As a UI designer, I want to design wireframes for the game so that we can visualize the user interface. | Design Wireframes | Wireframe Mockups created for all key game screens. | High | 5 | 1 | Team Member 1
UI Design | UI-2 | As a UI designer, I want to create interactive mockups so that we can test the user experience. | Create Mockups | Interactive UI Mockups created and tested with users. | High | 4 | 2 | Team Member 2
UI Design | UI-3 | As a UI designer, I want to develop a UI style guide so that the UI is consistent throughout the game. | Develop UI Style Guide | UI Style Guide Document created and approved by the development team. | Medium | 3 | 2 | Team Member 3
UI Design | UI-4 | As a UI designer, I want to design accessibility features so that the game is usable by people with disabilities. | Design Accessibility Features | Accessibility Compliance Report generated, highlighting compliance with accessibility standards. | Medium | 2 | 2 | Team Member 4
Frontend Development | FE-1 | As a developer, I want to implement the game board so that users can play the game. | Implement Game Board | Interactive Game Board rendered correctly in the browser. | High | 5 | 2 | Team Member 1
Frontend Development | FE-2 | As a developer, I want to implement move validation so that users can only make valid moves. | Implement Move Validation | Move Validation Logic implemented and tested. | High | 3 | 3 | Team Member 2
Frontend Development | FE-3 | As a developer, I want to implement win/draw detection so that the game can determine the winner. | Implement Win/Draw Detection | Win/Draw Detection Functionality implemented and tested. | High | 4 | 3 | Team Member 3
Frontend Development | FE-4 | As a developer, I want to implement turn management so that the game knows whose turn it is. | Implement Turn Management | Turn Management System implemented and tested. | High | 3 | 3 | Team Member 4
Frontend Development | FE-5 | As a developer, I want to implement the menu structure so users can navigate the game. | Implement Menu Structure | Functional Menu System implemented and tested. | Medium | 2 | 3 | Team Member 1
Frontend Development | FE-6 | As a developer, I want to implement the scoreboard so that users can see the score. | Implement Scoreboard | Functional Scoreboard implemented and displaying the score. | Medium | 2 | 4 | Team Member 2
Frontend Development | FE-7 | As a developer, I want to implement a settings panel so that users can customize the game. | Implement Settings Panel | Functional Settings Panel implemented and tested. | Low | 3 | 4 | Team Member 3
Frontend Development | FE-8 | As a developer, I want to implement a help section so that users can get assistance with the game. | Implement Help Section | Functional Help Section implemented and accessible to users. | Low | 2 | 4 | Team Member 4
Frontend Development | FE-9 | As a developer, I want to implement local player vs player mode so that two users can play locally. | Implement Local Player vs Player | Functional Player vs Player Game Mode implemented. | High | 4 | 4 | Team Member 1
Frontend Development | FE-10 | As a QA tester, I want to test player vs player functionality so that the game works as expected. | Test Player vs Player Functionality | Working Player vs Player Game Mode with no critical bugs. | High | 1 | 5 | Team Member 2
Frontend Development | FE-11 | As a developer, I want to implement basic AI logic for player vs AI mode. | Implement Basic AI Logic | Basic AI Opponent implemented and making reasonable moves. | Medium | 5 | 5 | Team Member 3
Frontend Development | FE-12 | As a QA tester, I want to test player vs AI functionality so that the game works as expected. | Test Player vs AI Functionality | Working Player vs AI Game Mode with no critical bugs. | Medium | 1 | 5 | Team Member 4
Backend Development (Optional) | BE-1 | As a developer, I want to set up local storage (if no DB) so that user data can be saved. | Set up Local Storage (if no DB) | Local Storage Implementation working and saving data. | Medium | 3 | 5 | Team Member 1
Backend Development (Optional) | BE-2 | As a database admin, I want to design a database schema (if DB) so that data can be stored efficiently. | Design Database Schema (if DB) | Database Schema Document created and reviewed. | Medium | 2 | 6 | Team Member 2
Backend Development (Optional) | BE-3 | As a backend developer, I want to implement API endpoints (if DB) so that the frontend can access data. | Implement API Endpoints (if DB) | Functional API Endpoints created and tested. | Medium | 5 | 6 | Team Member 3
Testing | T-1 | As a QA tester, I want to write unit tests for core logic so that code is robust. | Write Unit Tests for Core Logic | Unit Test Suite created for all core logic functions. | High | 4 | 6 | Team Member 4
Testing | T-2 | As a QA tester, I want to execute unit tests so that bugs are identified early. | Execute Unit Tests | Unit Test Results documented and issues addressed. | High | 2 | 6 | Team Member 1
Testing | T-3 | As a QA tester, I want to test UI and game logic integration so that everything works together. | Test UI and Game Logic Integration | Integration Test Report generated and issues addressed. | High | 3 | 7 | Team Member 2
Testing | T-4 | As a QA tester, I want to conduct UAT so that users can provide feedback. | Conduct UAT | UAT Feedback Report generated and issues prioritized. | High | 2 | 7 | Team Member 3
Testing | T-5 | As a developer, I want to address UAT feedback so that the application meets user needs. | Address UAT Feedback | Updated Application deployed with UAT feedback addressed. | High | 5 | 7 | Team Member 4
Deployment | D-1 | As a DevOps engineer, I want to configure a hosting environment so that the application can be deployed. | Configure Hosting Environment | Configured Hosting Environment ready for deployment. | High | 3 | 7 | Team Member 1
Deployment | D-2 | As a DevOps engineer, I want to set up a CI/CD pipeline so that deployments are automated. | Set up CI/CD Pipeline | CI/CD Pipeline Established for automated deployments. | High | 4 | 8 | Team Member 2
Deployment | D-3 | As a DevOps engineer, I want to deploy the application so that users can access it. | Deploy Application | Deployed Application accessible to users. | High | 1 | 8 | Team Member 3
Deployment | D-4 | As a DevOps engineer, I want to monitor application performance so that issues are detected. | Monitor Application Performance | Performance Monitoring Report generated and analyzed. | Medium | 2 | 8 | Team Member 4
Okta Integration (Optional) | OK-1 | As a security admin, I want to create an Okta tenant so that we can use Okta for authentication. | Create Okta Tenant | Okta Tenant Created and configured. | Low | 3 | 8 | Team Member 1
Okta Integration (Optional) | OK-2 | As a security admin, I want to configure the Okta app so that it integrates with our application. | Configure Okta App | Okta Application Configured with necessary settings. | Low | 4 | 9 | Team Member 2
Okta Integration (Optional) | OK-3 | As a developer, I want to implement the Okta SDK (Option 1) so that we can use Okta for authentication. | Implement Okta SDK (Option 1) | Okta SDK Integrated into the frontend. | Low | 5 | 9 | Team Member 3
Okta Integration (Optional) | OK-4 | As a developer, I want to implement session-based auth (Option 2) so that we can manage user sessions. | Implement Session-Based Auth (Option 2) | Session-Based Auth Implemented in the backend. | Low | 3 | 9 | Team Member 4
Okta Integration (Optional) | OK-5 | As a developer, I want to secure API endpoints (Option 1) so that only authenticated users can access them. | Secure API Endpoints (Option 1) | Secure API Endpoints using Okta authentication. | Low | 2 | 9 | Team Member 1
Documentation | DOC-1 | As a technical writer, I want to write a user manual so that users can understand how to use the application. | Write User Manual | User Manual written and reviewed. | Medium | 5 | 10 | Team Member 2
Documentation | DOC-2 | As a technical writer, I want to write API documentation (if DB) so that developers can use the API. | Write API Documentation (if DB) | API Documentation written and published. | Medium | 3 | 10 | Team Member 3
Documentation | DOC-3 | As a project manager, I want to prepare release notes so that users know what's new. | Prepare Release Notes | Release Notes prepared and published. | Medium | 2 | 10 | Team Member 4
Governance & Risk Management | GR-1 | As a project manager, I want to conduct weekly check-ins so that the project stays on track. | Conduct Weekly Check-Ins | Check-In Meeting Minutes documented weekly. | High | 1 | 10 | Team Member 1
Governance & Risk Management | GR-2 | As a project manager, I want to identify potential risks so that we can mitigate them. | Identify Potential Risks | Risk Assessment Report created and updated. | Medium | 3 | 11 | Team Member 2
Governance & Risk Management | GR-3 | As a project manager, I want to develop mitigation plans so that we can address potential risks. | Develop Mitigation Plans | Mitigation Plans Document created and reviewed. | Medium | 2 | 11 | Team Member 3
Reporting | REP-1 | As a developer, I want to implement a score summary feature so users can see their performance. | Implement Score Summary Feature | Functional Score Summary implemented and tested. | Low | 3 | 11 | Team Member 4
Reporting | REP-2 | As an analyst, I want to integrate with an analytics dashboard so we can track usage. | Integrate with Analytics Dashboard | Integrated Analytics Dashboard providing usage data. | Low | 5 | 11 | Team Member 1
Performance | PERF-1 | As a frontend developer, I want to optimize UI rendering so that the UI is smooth. | Optimize UI Rendering | Improved UI Rendering Performance verified. | Medium | 4 | 12 | Team Member 2
Performance | PERF-2 | As a developer, I want to optimize game logic so that the game runs efficiently. | Optimize Game Logic | Improved Game Logic Performance verified. | Medium | 3 | 12 | Team Member 3
Security | SEC-1 | As a security engineer, I want to secure local storage (if used) so data is protected. | Secure Local Storage (if used) | Secured Local Storage implementation verified. | High | 4 | 12 | Team Member 4
Security | SEC-2 | As a security engineer, I want to implement role-based access control (if Okta) so unauthorized actions are prevented. | Implement Role-Based Access Control (if Okta) | Role-Based Access Control Implemented and tested. | High | 3 | 12 | Team Member 1
Accessibility | ACC-1 | As a developer, I want to add keyboard navigation so the game is usable without a mouse. | Add Keyboard Navigation | Keyboard Navigation Functionality implemented and tested. | High | 2 | 13 | Team Member 2
Accessibility | ACC-2 | As a developer, I want to add screen reader text so that screen readers can read the game. | Add Screen Reader Text | Screen Reader Compatibility verified and improved. | High | 3 | 13 | Team Member 3
```