## Sheet1
Epic | ID | User Story | Tasks/Subtasks | Acceptance Criteria | Priority | Story Points | Sprint Number | Assignee | Start Date | End Date
Gameplay | 1 | As a player, I want to see a 3x3 grid so I can play Tic Tac Toe. | Create the 3x3 grid display; Style the grid with CSS. | The grid should be clearly visible and aesthetically pleasing; The grid should have 9 clickable cells. | High | 3 | 1 | Team Member 1 | 2025-08-19 | 2025-09-01
Gameplay | 2 | As a player, I want to be able to click on a cell to place my mark (X or O). | Implement cell click functionality; Determine current player's mark; Place the mark in the selected cell; Disable the cell after it's marked. | Clicking an empty cell places the correct player's mark; Marked cells cannot be changed; The display accurately shows the game state. | High | 5 | 1 | Team Member 2 | 2025-08-19 | 2025-09-01
Gameplay | 3 | As a player, I want the game to alternate turns between X and O. | Track current player; Switch players after each move; Update UI to indicate whose turn it is. | The game automatically alternates between X and O; The UI clearly indicates the current player's turn. | High | 3 | 1 | Team Member 3 | 2025-08-19 | 2025-09-01
Win Condition | 4 | As a player, I want the game to detect when a player has won. | Check for winning combinations after each move; Identify all possible winning combinations (rows, columns, diagonals). | The game correctly identifies a win when a player has three in a row; The game does not falsely identify a win. | High | 5 | 1 | Team Member 1 | 2025-08-19 | 2025-09-01
Win Condition | 5 | As a player, I want the game to declare the winning player. | Display a win message; Highlight the winning combination (optional). | The game displays a message declaring the winning player; The winning combination is visually distinct (optional). | High | 3 | 2 | Team Member 2 | 2025-09-02 | 2025-09-15
Draw Condition | 6 | As a player, I want the game to detect when the game is a draw. | Check if all cells are filled and no player has won. | The game correctly identifies a draw when all cells are filled and no one has won. | Medium | 3 | 2 | Team Member 3 | 2025-09-02 | 2025-09-15
Draw Condition | 7 | As a player, I want to be able to restart the game. | Implement a restart button; Reset the game board; Reset player turns. | Clicking the restart button resets the game board to its initial state; The game restarts with X's turn. | Medium | 2 | 2 | Team Member 1 | 2025-09-02 | 2025-09-15
Restart | 8 | As a player, I want the game to declare a draw. | Display a draw message. | The game displays a message indicating a draw. | Medium | 2 | 2 | Team Member 2 | 2025-09-02 | 2025-09-15
Error Handling | 9 | As a developer, I want error handling to prevent unexpected behavior. | Implement input validation; Implement try-catch blocks to handle exceptions. | The game handles invalid user inputs gracefully; The game does not crash due to unexpected errors. | Low | 2 | 3 | Team Member 3 | 2025-09-16 | 2025-09-29
Accessibility | 10 | As a player, I want the game to be accessible to users with disabilities. | Ensure the game is keyboard-navigable; Provide alternative text for images. | The game is fully navigable using a keyboard; Screen readers can accurately describe the game state. | Low | 5 | 3 | Team Member 1 | 2025-09-16 | 2025-09-29